## Sheet1
Plan: URSW Incubator Report
Task number | Task name | Start | End | Responsible | People Involved | Comments
I | Introduction | 2007-09-05 | 2007-09-30 | Paulo | Volunteers
II | Intent and Process | 2007-09-05 | 2007-10-07 | Paulo | Volunteers
II | Initial Ontology | 2007-09-05 | 2007-10-15 | Mitch | Volunteers
IV | Use Cases | 2007-09-05 | 2007-11-18 | Edit team | Use case managers | Will be split into subtasks. One writer per task
V | Benefits of Standardization | 2007-10-07 | 2007-12-12 | ? | Volunteers
VI | Recommendations | 2007-12-12 | 2008-02-10 | Edit Team | Volunteers