# DAISY Consortium

Registered as an Association under the civil code of Switzerland

Jesper Kline, President

President@daisy.org

Avneesh Singh, Chief Operating Officer

Email: asingh@daisy.org

Phone: +91 99100 58818

www.daisy.org

# Progress Report

# EPUBCheck Development & Maintenance

Submitted to: Publishing Steering Committee

Date: April 29, 2019

## Summary

The phase 1 of the project, focused on updating EPUBCheck to EPUB 3.2 has been completed as per the schedule. To allow proper feedback from the publishing industry, the stable production-ready release was kept on hold for a month as per the decision of the Steering Committee representatives. This marks a major milestone of the project, providing a robust base for adoption of EPUB 3.2 specifications.

While new EPUBCheck 4.2 was being developed, the older version of EPUBCheck conforming to EPUB 3.0.1 was maintained. A maintenance version, 4.1.1 was released with bug fixes and updated localized messages in Jan 2019.

In addition to the milestones defined in the statement of work, the online EPUB validator is also updated to the EPUB 4.1.1 maintenance release.

## Details of completed milestones

Note: The timelines modified based on the decisions of the Steering Committee representatives are marked by *.

| Milestones | Schedule as per SOW/SC | Completion date | Description |
| --- | --- | --- | --- |
| Milestone 1.1: Maintenance release (EPUBCheck 4.1). | Oct/Nov 2018 | Nov 26, 2018 | The maintenance release addressed important pending issues before commencing changes for adding EPUB 3.2 support. The details of bug fixes, changes and downloads are available at the EPUBCheck 4.1.0 release page. |
| 1st test release for Milestone 1.2: (Implementation of EPUB 3.2) | Jan 2019 | Jan 14, 2019 | The test release updates the schemas for Package Documents and Content Documents. EPUBCheck now uses the latest schemas from the Nu Html Checker, which are kept up-to-date with latest changes in HTML standard. Further details and downloads are available at the EPUBCheck 4.2.0 alpha 1 release page. |
| Maintenance release v4.1.1 of EPUBCheck for EPUB 3.0.1 | As per the requirement | Jan 22, 2019 | The maintenance release is focused on bug fixes and updating the localized messages contributed by the volunteers. Brazilian-Portuguese and Korean languages are introduced, and French, German, Italian, Japanese and Spanish are updated. Further details and downloads are available at EPUBCheck 4.1.1 release page. |
| 2nd test release for Milestone 1.2: (Implementation of EPUB 3.2) | Feb 2019 | Feb 25, 2019 | Support for EPUB 3.2 is nearly complete with the beta release. It includes updates to the various EPUB vocabularies (for epub:type and Package Document properties), support for new Core Media Types, various bug fixes and other small improvements. Further details and downloads are available at V4.2 beta release page. |
| Release candidate for Milestone 1.2: (Implementation of EPUB 3.2) | Not defined in SOW* | Mar 18, 2019 | The release featured complete support of EPUB 3.2 and was the last test release before the final release. For details and downloads please visit EPUBCheck 4.2-RC page |
| EPUBCheck 4.2 release, with complete support for EPUB 3.2 | April 2019* | April 23, 2019 | V4.2 is the stable production-ready release providing complete support for EPUB 3.2. It is localized in Danish, French, German, Italian, Japanese, Korean, & Spanish. Based on decision made by steering committee representatives, the release was kept on hold for a month to allow more time for feedback. For further details and downloads please visit EPUBCheck 4.2 release page. |

### Additional milestones achieved (beyond that are defined in the statement of work)

Based on decision made by representatives of Steering Committee for EPUBCheck project (Tzviya and Luc), the online EPUB validator service http://validator.idpf.org/ was updated to EPUB 4.1.1 (The latest maintenance release of EPUBCheck conforming to EPUB 3.0.1).

## Work in Progress

- Planning of Phase 2 of the project.

Sincerely

Avneesh Singh

Chief Operating Officer, DAISY Consortium