## Timeline without CFC
TTML WG specifications Timeline without CFC (tight timeline) |  | status |  | status |  | status |  | status
Specifications | TTML2 |  | TTML1 |  | IMSC1.1 |  | WebVTT
URL | https://www.w3.org/TR/ttml2/ |  | https://www.w3.org/TR/ttml1/ |  | https://www.w3.org/TR/ttml-imsc1.1/ |  | http://www.w3.org/TR/webvtt1/
CR Timeline
Author sends editor's draft for review | 2018-07-23 | done | 2018-07-17 | done | 2018-07-03 | done
Chair sends CfC (14 days period) | 2018-07-24 | done | 2018-07-17 | done | 2018-07-03 | done
end of CfC | 2018-08-07 |  | 2018-07-31 | done | 2018-07-17 | done
Author sends final document | 2018-08-07 |  | 2018-08-01 | done | 2018-07-18 | done
Staff checks and upload spec to final destination on TR | 2018-08-07 |  | 2018-08-01 | done | 2018-07-19 | done
Staff sends Transition request to director (needs about a week for approval) | 2018-08-07 |  | 2018-08-02 | done | 2018-07-19 | done
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-08-13 |  | 2018-08-07 |  | 2018-07-24 | done
Staff sends annoucement draft to com team | 2018-08-13 |  | 2018-08-07 |  | 2018-07-24 | done
CR publication | 2018-08-14 |  | 2018-08-09 |  | 2018-07-26 | done
start of a 60 days exclusion opportunity | 2018-08-14 |  | 2018-08-09 |  | 2018-07-26 | done
PR Timeline
Dealine for comments | 2018-09-11 |  | 2018-09-06 |  | 2018-08-23
Author sends editor's draft for review | 2018-09-12 |  | 2018-09-07 |  | 2018-08-27
Chair sends CfC (14 days period) | N/A ?? |  | N/A ?? |  | N/A ??
end of CfC | N/A ?? |  | N/A ?? |  | N/A ??
Author sends final document | 2018-09-16 |  | 2018-09-17 |  | 2018-08-28
Testsuite and Implementation report finalysed | 2018-09-16 |  | 2018-09-17 |  | 2018-08-28
Staff checks and upload spec to final destination on TR | 2018-09-17 |  | 2018-09-17 |  | 2018-08-29
Staff sends PR Transition request to director (needs about a week for approval) | 2018-09-18 |  | 2018-09-18 |  | 2018-08-30
Staff prepares Questionnaire@@@ | 2018-09-24 |  | 2018-09-24 |  | 2018-09-04
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-09-24 |  | 2018-09-24 |  | 2018-09-04
Staff sends annoucement draft to com team | 2018-09-24 |  | 2018-09-24 |  | 2018-09-04
PR publication | 2018-09-25 |  | 2018-09-25 |  | 2018-09-06
Last day of the 150 days exclusion opportunity | 2018-10-07 |  | 2018-10-07 |  | 2018-09-23
Last day of the 60 days exclusion opportunity | 2018-10-13 |  | 2018-10-08 |  | 2018-09-24
Last day of the AC Review | 2018-10-23 | 28 | 2018-10-23 | 28 | 2018-10-04
REC Timeline
Chair sends CfC (14 days period) | N/A ?? |  | N/A ?? |  | N/A ??
end of CfC | N/A ?? |  | N/A ?? |  | N/A ??
Author sends final document | 2018-10-23 |  | 2018-10-23 |  | 2018-10-04
Staff checks and upload spec to final destination on TR | 2018-10-23 |  | 2018-10-24 |  | 2018-10-05
Staff sends REC Transition request to director (needs about a week for approval) | 2018-10-24 |  | 2018-10-24 |  | 2018-10-05
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-10-29 |  | 2018-10-29 |  | 2018-10-10
Staff sends annoucement draft to com team | 2018-10-29 |  | 2018-10-29 |  | 2018-10-10
REC publication | 2018-10-30 |  | 2018-10-30 |  | 2018-10-11
| https://w3c.github.io/spec-releases/milestones/?cr=2018-08-16&noFPWD=true |  |  |  | https://w3c.github.io/spec-releases/milestones/?cr=2018-07-26&noFPWD=true
https://w3c.github.io/spec-releases/milestones/?cr=2018-08-09&noFPWD=true
Comments & notes
See also https://www.w3.org/wiki/TimedText/Publications. CMAF 23000-19 depends on it. Needs to be done by October.
https://w3c.github.io/spec-releases/milestones/?cr=2018-08-07&noFPWD=true
https://w3c.github.io/spec-dashboard/?34314
https://ethercalc.org/no163r5i5dxv
The upcoming 2018 moratoria on publications
From July 30th, 2018 to August 3rd, 2018 : Summer
From October 22nd, 2018 to October 26th, 2018 : TPAC 2018
From December 24th, 2018 to January 1st, 2019 : End of Year

## Timeline with PR CfC
TTML WG specifications Timeline with PR CfC (tight timeline) |  | status |  | status |  | status |  | status
Specifications | TTML2 |  | TTML1 |  | IMSC1.1 |  | WebVTT
URL | https://www.w3.org/TR/ttml2/ |  | https://www.w3.org/TR/ttml1/ |  | https://www.w3.org/TR/ttml-imsc1.1/ |  | http://www.w3.org/TR/webvtt1/
CR Timeline
Author sends editor's draft for review | 2018-07-23 | done | 2018-07-17 | done | 2018-07-03 | done
Chair sends CfC (14 days period) | 2018-07-24 | done | 2018-07-17 | done | 2018-07-03 | done
end of CfC | 2018-08-07 |  | 2018-07-31 | done | 2018-07-17 | done
Author sends final document | 2018-08-07 |  | 2018-08-01 | done | 2018-07-18 | done
Staff checks and upload spec to final destination on TR | 2018-08-07 |  | 2018-08-01 | done | 2018-07-19 | done
Staff sends Transition request to director (needs about a week for approval) | 2018-08-07 |  | 2018-08-02 | done | 2018-07-19 | done
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-08-13 |  | 2018-08-07 |  | 2018-07-24 | done
Staff sends annoucement draft to com team | 2018-08-13 |  | 2018-08-07 |  | 2018-07-24 | done
CR publication | 2018-08-14 |  | 2018-08-09 |  | 2018-07-26 | done
start of a 60 days exclusion opportunity | 2018-08-14 |  | 2018-08-09 |  | 2018-07-26 | done
PR Timeline
Dealine for comments | 2018-09-11 |  | 2018-09-06 |  | 2018-08-23
Author sends editor's draft for review | 2018-09-12 |  | 2018-09-07 |  | 2018-08-24
Chair sends CfC (14 days period) | 2018-09-12 |  | 2018-09-07 |  | 2018-08-24
end of CfC | 2018-09-26 |  | 2018-09-21 |  | 2018-09-07
Author sends final document | 2018-09-27 |  | 2018-09-24 |  | 2018-09-10
Testsuite and Implementation report finalysed | 2018-09-27 |  | 2018-09-24 |  | 2018-09-10
Staff checks and upload spec to final destination on TR | 2018-09-28 |  | 2018-09-25 |  | 2018-09-11
Staff sends PR Transition request to director (needs about a week for approval) | 2018-09-28 |  | 2018-09-25 |  | 2018-09-11
Staff prepares Questionnaire | 2018-10-01 |  | 2018-10-01 |  | 2018-09-17
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-10-03 |  | 2018-10-01 |  | 2018-09-17
Staff sends annoucement draft to com team | 2018-10-03 |  | 2018-10-01 |  | 2018-09-17
PR publication | 2018-10-04 |  | 2018-10-02 |  | 2018-09-18
Last day of the 150 days exclusion opportunity | 2018-10-07 |  | 2018-10-07 |  | 2018-09-23
Last day of the 60 days exclusion opportunity | 2018-10-13 |  | 2018-10-08 |  | 2018-09-24
Last day of the AC Review | 2018-11-01 |  | 2018-10-30 |  | 2018-10-16
REC Timeline
Chair sends CfC (14 days period) | N/A ?? |  | N/A ?? |  | N/A ??
end of CfC | N/A ?? |  | N/A ?? |  | N/A ??
Author sends final document | 2018-11-05 |  | 2018-10-31 |  | 2018-10-17
Staff checks and upload spec to final destination on TR | 2018-11-05 |  | 2018-10-31 |  | 2018-10-17
Staff sends REC Transition request to director (needs about a week for approval) | 2018-11-05 |  | 2018-11-01 |  | 2018-10-18
Staff sends Publication request to webmaster (needs 1 or 2 days ahead of publication) | 2018-11-12 |  | 2018-11-07 |  | 2018-10-24
Staff sends annoucement draft to com team | 2018-11-12 |  | 2018-11-07 |  | 2018-10-24
REC publication | 2018-11-13 |  | 2018-11-08 |  | 2018-10-30 | (25 oct is moratoria on publications)
Comments & notes
See also https://www.w3.org/wiki/TimedText/Publications. CMAF 23000-19 depends on it. Needs to be done by October.
https://w3c.github.io/spec-releases/milestones/?cr=2018-08-07&noFPWD=true
https://w3c.github.io/spec-dashboard/?34314
https://ethercalc.org/no163r5i5dxv
The upcoming 2018 moratoria on publications
From July 30th, 2018 to August 3rd, 2018 : Summer
From October 22nd, 2018 to October 26th, 2018 : TPAC 2018
From December 24th, 2018 to January 1st, 2019 : End of Year
Formulas:
TTML2 = [TTML2, row above]+14
TTML1 = [TTML1, row above]+14
IMSC1.1 = [IMSC1.1, row above]+14